## OWN
FIRST QUARTER ( JULY - SEPTEMBER, 2016) PROGRESS REPORT FOR THE FINANCIAL YEAR 2016/2017
OWN SOURCE FUND
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
SECTION No: 5000A Name: General Administration
SUB VOTE No: 5000 |  | SUB VOTE NAME: Administration and General
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To facilitate the council being a member of local governinment authority bank by June2017 |  |  | √ |  |  | 36000000 |  | 0
[5 empty] | Total for Section | [5 empty] | 36000000 |  | 0
SECTION No: 502D Name: Finance-Revenue
SUB VOTE No: 5000 |  | SUB VOTE NAME: Administration and General
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | Tofacilitate Implementation of lower level development projects by returning 20% of own source revenue collection by June 2017 |  |  | √ |  |  | 210648000 |  | 0
[5 empty] | Total for Section | [5 empty] | 210648000 |  | 0
SECTION No: 502E Name: Trade and Markets operations
SUB VOTE No: 5000 |  | SUB VOTE NAME: Administration and General
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D02D01 | √ | √ | √ | √ | To support construction of toilet and installation water system in new timber market at Idofi by June 2017 |  |  | √ |  |  | 13300000 |  | 0
[5 empty] | Total for Section | [5 empty] | 13300000 |  | 0
SECTION No: 503B Name: Policy and Planning
SUB VOTE No: 5005 |  | SUB VOTE NAME: Policy and Planning
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To facilitates monitoring and supervision of Development Projects and LAAC reports preparation by June 2017 |  |  | √ |  |  | 25378600 | 4924500 | 19.4041
[5 empty] | Total for Section | [5 empty] | 25378600 |  | 19.4041
SECTION No: 506B: Name: Agriculture Operations
SUB VOTE No: 5033 |  | SUB VOTE NAME: Agriculture
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To design structure of Lyamkena grain market by June, 2017 |  |  | √ |  |  | 28163400 |  | 0
D01D03 | √ | √ | √ | √ | To support farmers with 5000 avocado seedlings by June, 2017 |  |  | √ |  |  | 10000000 |  | 0
[5 empty] | Total for Section | [5 empty] | 38163400 |  | 0
SECTION No: 507B Name: Primary Education Operations
SUB VOTE No: 5007 |  | SUB VOTE NAME: Primary Education
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D02D01 | √ | √ | √ | √ | To support construction 2 classrooms and 1 office at 5 on going new primary school (Kahawa,Kwauchungu, Mlenga, Magegere and Maguvani) by Juni 2017 |  |  | √ |  |  | 20000000 |  | 0
D01D02 | √ | √ | √ | √ | To support construction of 1 hostel building at Kahawa special school by June,2017 |  |  | √ |  |  | 25000000 |  | 0
D01D03 | √ | √ | √ | √ | To support contruction 2 classrooms and 1 office in Mfumbi new Primary School by June,2017 |  |  | √ |  |  | 5000000 |  | 0
[5 empty] | Total for Section | [5 empty] | 50000000 |  | 0
SECTION No: 508A Name: Council Hospital Services
SUB VOTE No: 5010 |  | SUB VOTE NAME: Health Services
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: A |  | OBJECTIVE DESCRIPTION: Improve services and reduce HIV/AIDS infection
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
AO2SO1 | √ | √ | √ | √ | To facilitate core funding of (10%) HSBF in improving provision of health services in the council by 2017 |  |  | √ |  |  | 14599900 |  | 0
AO2SO2 | √ | √ | √ | √ | To construct 9 New dispensaries according to MOH facility technical design with water tanks, serewage system and wate disposal in 9 villages (Mahongole, Ibatu, Mtanga, Ngamanga, Ikwete, Utengule, Mtulingala, Usetule and Maguvani) by June 2017 |  |  | √ |  |  | 30400100 |  | 0
[5 empty] | Total for Section | [5 empty] | 45000000 |  | 0
SECTION No: 509B: Name: Secondary Education Operations
SUB VOTE No: 5008 |  | SUB VOTE NAME: SECONDARY EDUCATION OPERATION
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
DO2D01 | √ | √ | √ | √ | To Support construction of 2 classroom at Deo Sanga Secondary School by June 2017 |  |  | √ |  |  | 7000000 |  | 0
DO2D02 | √ | √ | √ | √ | To Support of construction of 1 classroom at Mlowa Secondary School by June 2017 |  |  | √ |  |  | 6000000 |  | 0
DO2D03 | √ | √ | √ | √ | To Support construction of 2 classrooms at kitandililo Secondary School by June 2017 |  |  | √ |  |  | 5000000 |  | 0
DO2D04 | √ | √ | √ | √ | To support construction of 80 students desks and chairs at Deo Sanga Secondary School by June 2017 |  |  | √ |  |  | 5000000 |  | 0
DO2D05 | √ | √ | √ | √ | To support construction of 80 students desks and chairs at Mlowa Secondary School by June 2017 |  |  | √ |  |  | 5000000 |  | 0
DO2D06 | √ | √ | √ | √ | To support construction of 50 students desks and chairs at Kitandilio Secondary School by June 2017 |  |  | √ |  |  | 3000000 |  | 0
DO2D07 | √ | √ | √ | √ | To support construction of 30 students desks and chairs at Makambako Secondary School by June 2017 |  |  | √ |  |  | 2000000 |  | 0
[5 empty] | Total for Section | [5 empty] | 33000000 |  | 0
SECTION No: 510B Name: Urban Water Supply
SUB VOTE No: 5018 |  | SUB VOTE NAME: Urban Water Supply
PROJECT CODE: 2216 |  | PROJECT NAME: Urban Water Supply and Sewerage
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent | Remarks on Implementation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To Support MAKUWASA to drill borehole and pump installation at Kivavi area (HLG) bya June 2017 |  |  | √ |  |  | 35000000 |  | 0
D01D02 | √ | √ | √ | √ | To support MAKUWASA To install 2 submersible pumps by June 2017 |  |  | √ |  |  | 17000000 |  | 0
D01D03 | √ | √ | √ | √ | To support MAKUWASA to install surface pump,sump well amd pump house maintenance (HLG) By June 2017 |  |  | √ |  |  | 30000000 |  | 0
[5 empty] | Total for Section | [5 empty] | 82000000
SECTION No: 511A Name: Works and Fire rescure Administration
SUB VOTE No: 5014 |  | SUB VOTE NAME: Works
PROJECT CODE: 2216 |  | PROJECT NAME: Urban Water Supply and Sewerage
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent | Remarks on Implementation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To support bus stand rehabilitation at Makambako bus stand by June 2017 |  |  | √ |  |  | 100000000 |  | 0
D01D02 | √ | √ | √ | √ | To support rehabilitation of lorry packing at majengo street by June, 2017 |  |  | √ |  |  | 20000000 |  | 0
[5 empty] | Total for Section | [5 empty] | 120000000 |  | 0
SECTION No: 512A: Name: Land and Natural Resource Administration
SUB VOTE No: 5009 |  | SUB VOTE NAME: Land Development & Urban Planning
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent | Remarks on Implementation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To facilitate land compasation payment by June, 2017 |  |  | √ |  |  | 25000000 |  | 0
D02D01 | √ | √ | √ | √ | To facilitate preparation of makambako Town Council Master plan by June 2017 |  |  | √ |  |  | 100000000 |  | 0
[5 empty] | Total for Section | [5 empty] | 125000000 |  | 0
SECTION No: 518B Name: Information Communication and Technology
SUB VOTE No: 5005 |  | SUB VOTE NAME: Informaton Communication and Technology
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: C |  | OBJECTIVE DESCRIPTION: Improve access, quality and equitable social services delivery
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent | Remarks on Implementation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
C01S01 | √ | √ | √ | √ | To facilitate installation of LGRCIS by June 2017 |  |  | √ |  |  | 3780000 |  | 0
[5 empty] | Total for Section | [5 empty] | 3780000 |  | 0
SECTION No: 527A: Name :Community Develiopment,Youth and Sosocial wellfare Administration.
SUB VOTE No: 5027 |  | SUB VOTE NAME: Comm Dvt,Gender and Children
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: C |  | OBJECTIVE DESCRIPTION: Improve access, quality and equitable social services delivery
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent | Remarks on Implementation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
C01D01 | √ | √ | √ | √ | To provide loans to 40 women and 20 youth development groups by June, 2017 |  |  | √ |  |  | 156454000 |  | 0
[5 empty] | Total for Section | [5 empty] | 156454000 |  | 0
[5 empty] | Grant Total - Own Source | [5 empty] | 938724000 |  | 19.4041

## LGDG
FIRST QUARTER ( JULY - SEPTEMBER, 2016) PROGRESS REPORT FOR THE FINANCIAL YEAR 2016/2017
LOCAL GOVERNMENT DEVELOPMENGT GRANT [LGDG-CDG]
VOTE CODE: 54 |  |  |  |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  |  |  |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
PERIOD COVERED: |  |  |  |  | Quarter ending September,2016 in the Financial Year 2016/2017
SECTION No: 503B Name: Policy and Planning
SUB VOTE No: 5005 |  |  |  |  | SUB VOTE NAME: Policy and Planning
PROJECT CODE: 3218 |  |  |  |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  |  |  |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D02 | √ | √ | √ | √ | To facilitate M & E of Council's development projects [LLG] by June, 2017 |  |  | √ |  |  | 21771850 | 0 | 0
[5 empty] | Total for Section | [5 empty] | 21771850 |  | 0
SECTION No: 5000A Name: General Administration
SUB VOTE No: 5000 |  |  |  |  | SUB VOTE NAME: Administration and General
PROJECT CODE: 3218 |  |  |  |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  |  |  |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D02D01 | √ | √ | √ | √ | To complete construction of Makambako Town administration block by June, 2017 |  |  | √ |  |  | 750000000 | 0 | 0
D02D02 | √ | √ | √ | √ | To support completion of construction of Mjimwema Ward Office [LLG] by June, 2017 |  |  | √ |  |  | 9094787 |  | 0
[5 empty] | Total for Section | [5 empty] | 759094787 |  | 0
SECTION No: 506B Name: Agriculture Operations
SUB VOTE No: 5033 |  |  |  |  | SUB VOTE NAME: Agriculture
PROJECT CODE: 3218 |  |  |  |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  |  |  |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D02 | √ | √ | √ | √ | To construct 1 modal structure of Lyamkena grain market [HLG] by June, 2017 |  |  | √ |  |  | 30000000 |  | 0
[5 empty] | Total for Section | [5 empty] | 30000000 |  | 0
SECTION No: 507B Name: Primary Education Operations
SUB VOTE No: 5007 |  |  |  |  | SUB VOTE NAME: Primary Education
PROJECT CODE: 3218 |  |  |  |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  |  |  |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D02D01 | √ | √ | √ | √ | To support construction 2 classrooms and 1 office at Kahawa primary school [LLG] by June,2017 |  |  | √ |  |  | 18209588 |  | 0
D02D02 | √ | √ | √ | √ | To support construction 2 classrooms and 1 office at Kwauchungu primary school [LLG]by June,2017 | [5 empty] | 4190597 |  | 0
D02D03 | √ | √ | √ | √ | To support construction 2 classrooms and 1 office at Maguvani new Primary School by June,2017 | [5 empty] | 11080219 |  | 0
D02D04 | √ | √ | √ | √ | To support construction 1 teacher's house at Mahongole Primary School by June,2017 | [5 empty] | 7019209 |  | 0
D02D05 | √ | √ | √ | √ | To support construction 1 teacher's house at Jududi Primary School [LLG] by June,2017 | [5 empty] | 6703361 |  | 0
D02D06 | √ | √ | √ | √ | To support construction 2 classrooms and 1 office at Ngamanga Primary School [LLG] by June,2017 | [5 empty] | 10331633 |  | 0
D02D07 | √ | √ | √ | √ | To support completion of construction 2 classrooms at Mwembetogwa 'B' Primary School [LLG] by June,2017 | [5 empty] | 2222395 |  | 0
D02D08 | √ | √ | √ | √ | To support construction 2 classrooms and 1 office at Maendeleo Primary School [LLG] by June,2017 | [5 empty] | 8209588 |  | 0
D02D09 | √ | √ | √ | √ | To support construction 2 classrooms and 1 office at Magegere new Primary School [LLG] by June,2017 | [5 empty] | 6000000 |  | 0
D02D10 | √ | √ | √ | √ | To support 39 primary schools with 400 desks [HLG] by June, 2017 | [5 empty] | 24166775 |  | 0
D02D11 | √ | √ | √ | √ | To support completion of construction 2 classrooms at Mwembetogwa 'A' Primary School [LLG] by June,2017 | [5 empty] | 5000000 |  | 0
D02D12 | √ | √ | √ | √ | To support construction of 2 classroom at Mlowa Primary school by June,2017 | [5 empty] | 3000000 |  | 0
[5 empty] | Total for section | [5 empty] | 106133365 |  | 0
SECTION No: 5010 Name: HEALTH SERVICES
SUB VOTE No: 508B |  |  |  |  | SUB VOTE NAME: Council Hospital Services
PROJECT CODE: 3218 |  |  |  |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  |  |  |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D02 | √ | √ | √ | √ | To complete construction of maternity complex ward [HLG] by June, 2017 |  |  | √ |  |  | 132663900 |  | 0
[5 empty] | Total for Section | [5 empty] | 132663900 |  | 0
SECTION No: 5012 Name: HEALTH CENTRES
SUB VOTE No: 508D |  |  |  |  | SUB VOTE NAME: Health Centres
PROJECT CODE: 5484 |  |  |  |  | PROJECT NAME: Primary Health Care
OBJECTIVE CODE: D |  |  |  |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D02 | √ | √ | √ | √ | To complete construction of Lyamkena Health Centre (LLG) by June 2017 |  |  | √ |  |  | 15717750 |  | 0
[5 empty] | Total for Section | [5 empty] | 15717750 |  | 0
SECTION No: 508E Name: DISPENSARIES
SUB VOTE No: 5013 |  |  |  |  | SUB VOTE NAME: Dispensaries
PROJECT CODE: 5484 |  |  |  |  | PROJECT NAME: Primary Health Care
OBJECTIVE CODE: D |  |  |  |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D05 | √ | √ | √ | √ | To support construction of Mahongole Dispensary By june 2017 |  |  | √ |  |  | 6000000 |  | 0
D01D06 | √ | √ | √ | √ | To support construction of Ibatu Dispensary By june 2017 |  |  | √ |  |  | 5000000 |  | 0
D01D07 | √ | √ | √ | √ | To support construction of Majengo Dispensary By June 2017 |  |  | √ |  |  | 4190597 |  | 0
D01D08 | √ | √ | √ | √ | To support construction of Usetule Dispensary By June 2017 |  |  | √ |  |  | 6000000 |  | 0
D01D09 | √ | √ | √ | √ | To support construction of Ngamanga Dispensary By June 2017 |  |  | √ |  |  | 5500000 |  | 0
D01D10 | √ | √ | √ | √ | To support construction of Mtulingala Dispensary By June 2019 |  |  | √ |  |  | 5500000 |  | 0
D01D11 | √ | √ | √ | √ | To support construction of Mtanga Dispensary By June 2017 |  |  | √ |  |  | 5000000 |  | 0
D01D12 | √ | √ | √ | √ | To support construction of Ikwete Dispensary By June 2017 |  |  | √ |  |  | 5000000 |  | 0
D01D13 | √ | √ | √ | √ | To support construction of Maguvani Dispensary By June 2021 |  |  | √ |  |  | 6000000 |  | 0
D01D14 | √ | √ | √ | √ | To support construction of Mkolango Dispensary By June 2022 |  |  | √ |  |  | 7000000 |  | 0
D01D15 | √ | √ | √ | √ | To support construction of Utengule Dispensary By June 2017 |  |  | √ |  |  | 5000000 |  | 0
D01D16 | √ | √ | √ | √ | To support construction of Kivavi Dispensary By June 2017 |  |  | √ |  |  | 6000000 |  | 0
[5 empty] | Total for section | [5 empty] | 66190597 |  | 0
SECTION No: 509B Name: SECONCONDARY EDUCATION OPERATIONS
SUB VOTE No: 5008 |  |  |  |  | SUB VOTE NAME:Secondary Education
PROJECT CODE: 3218 |  |  |  |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  |  |  |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
DO3D04 | √ | √ | √ | √ | To Support construction of 2 classroom at DeoSanga Secondary School [LLG] by June 2017 |  |  | √ |  |  | 6209588 |  | 0
DO3D05 | √ | √ | √ | √ | To Support of construction of 2 classroom at Mlowa Secondary School [LLG] by June 2017 |  |  | √ |  |  | 7829100 |  | 0
DO3D06 | √ | √ | √ | √ | To Support construction of 2 classrooms at kitandililo Secondary School [LLG] by June 2017 |  |  | √ |  |  | 9822063 |  | 0
DO3D07 | √ | √ | √ | √ | To Support construction of 2 classrooms at Kipagamo Secondary School [LLG] by June 2017 |  |  | √ |  |  | 10000000 |  | 0
[5 empty] | Total for section | [5 empty] | 33860751 |  | 0
SECTION No: 510B Name: Urban Water Supply
SUB VOTE No: 5018 |  |  |  |  | SUB VOTE NAME: Urban Water Supply
PROJECT CODE: 2216 |  |  |  |  | PROJECT NAME: Urban Water Supply and Sewerage
OBJECTIVE CODE: D |  |  |  |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
DO1D04 | √ | √ | √ | √ | To Support MAKUWASA to drill borehole and pump installation at Kivavi area (HLG) bya June 2017 |  |  | √ |  |  | 15000000 |  | 0
DO1D05 | √ | √ | √ | √ | To support MAKUWASA to install surface pump,sump well and pump house maintenance (HLG) By June 2017 |  |  | √ |  |  | 5000000 |  | 0
[5 empty] | Total for section | [5 empty] | 20000000 |  | 0
[5 empty] | TOTAL CDG | [5 empty] | 1185433000 |  | 0

## SEDP
FUNDER SECONDARY EDUCATION DEVELOPMENT PROGRAM (SEDP)
SECTION No: 509B: Name: Secondary Education Operations
VOTE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
SUB VOTE No: 5008 |  | SUB VOTE NAME: Secondary Education
PROJECT CODE: 4390 |  | PROJECT NAME: SECONDARY EDUCATION DEVELOPMENT PROGRAMME
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To Support construction of Toilets at Kipagamo Secondary School by June 2017 |  |  | √ |  |  | 10000000 |  | 0
D01D02 | √ | √ | √ | √ | To Support of construction of 4 classrooms at 3 Secondary Schools (2-DeoSanga, 1-Lyamkena and 1-Mlowa) by June 2017 |  |  | √ |  |  | 60000000 |  | 0
D01D03 | √ | √ | √ | √ | To Support construction of 1 Domitory at Makambako Secondary School by June 2017 |  |  | √ |  |  | 30000000 |  | 0
D01D04 | √ | √ | √ | √ | To support construction of 3 Hostels at 3 Secondary Schools (1-Mahongole, 1- Makambako and 1-Mlowa) by June 2017 |  |  | √ |  |  | 30000000 |  | 0
D01D05 | √ | √ | √ | √ | To support construction of gas and water system to 6 Secondary School laboratories (DeoSanga, Kipagamo, Kitandililo, Lyamkena, Mlowa and Mukilima)by June 2017 |  |  | √ |  |  | 10704000 |  | 0
D01D06 | √ | √ | √ | √ | To support making of 40 Hostel beds s at Kitandilio Secondary School by June 2017 |  |  | √ |  |  | 10000000 |  | 0
D01D07 | √ | √ | √ | √ | To support construction of 4 Conference halls at 4 Secondary Schools (DeoSanga, Kipagamo, Kitandililo and Mukilima) l by June 2017 |  |  | √ |  |  | 30000000 |  | 0
D01D08 | √ | √ | √ | √ | To support construction of 3 teacher's house at Mtimbwe,Kitandililo and Mahongole Secondary School by June 2017 |  |  | √ |  |  | 81000000 |  | 0
[5 empty] | Total for section | [5 empty] | 261704000 |  | 0

## ROAD FUND
FUNDER ROAD FUND
SECTION No: 511B: Name: Road Services
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SUB VOTE No: 5014 |  | SUB VOTE NAME: Works
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
PROJECT CODE: 4101 |  | PROJECT NAME: Road Sector Programme Support
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01S01 | √ | √ | √ | √ | To carryout 39.2 Km of routine maintanance at (Kiumba street 3km, Kivavi ward street roads 6km, Majengo street roads 3km, Maguvani ward street roads 3km and Mjimwema ward street roads 3km) Mlowa- idofi 11.2km and Ngamanga-Ikwete 10km by June 2017 |  |  | √ |  |  | 117600000 |  | 0
D01S02 | √ | √ | √ | √ | To carry out 12 Km of spot improvement at Mlowa-Mkolango- Manga by June 2017 |  |  | √ |  |  | 42454000 |  | 0
D01S03 | √ | √ | √ | √ | To carry out 10 Km of periodic maintanance at Usetule- Kitandililo and construction of 1.6km of storm water drainage at Makambako Town roads by June 2017 |  |  | √ |  |  | 444226002 |  | 0
D02S01 | √ | √ | √ | √ | To costruct 3 bridges (Ibatu Kitandililo, Luhota-Ngamanga bridges, Ikwete-Mashujaa) by June 2017 |  |  | √ |  |  | 190000000 |  | 0
D02S02 | √ | √ | √ | √ | Follow up and supervision of roads and bridges construction by June 2017 |  |  | √ |  |  | 52529998 |  | 0
[5 empty] | Total for section | [5 empty] | 846810000 |  | 0
[5 empty] | Total Road Fund | [5 empty] | 846810000

## NMSF
FUNDER NATIONAL MULTISECTORAL STRATEGIC FUND (NMSF)
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 5492 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SECTION No: 527B: Name :Community Development,Gender and Children
SUB VOTE No: 5027 |  | SUB VOTE NAME: Comm Dvt,Gender and Children
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
PROJECT CODE: 5492 |  | PROJECT NAME: Tanzania Multisectoral HIV/AIDS Project
OBJECTIVE CODE:A |  | OBJECTIVE DESCRIPTION: Improve Services and reduce HIV/AIDS Project
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
A01S01 | √ | √ | √ | √ | To conduct one day refresher training to WMAC on the roles and responsibilitie in 8 Wards and disserminate new guideline on the formation of HIV/AIDs Committee at 4wards by June,2017. |  |  | √ |  |  | 5137000 |  | 0
A01S02 | √ | √ | √ | √ | To sensitize the community on HIV/AIDS prevention at 19 Streets/villages through cinema show by June, 2017 |  |  | √ |  |  | 3744000 |  | 0
A01S03 | √ | √ | √ | √ | To facilitate internal audit in conducting semi annual and annual HIV/AIDS NMSF projects by June,2017 |  |  | √ |  |  | 1610000 |  | 0
A01S04 | √ | √ | √ | √ | To sensitize 50 sex workers and barmaids in 3wards on interpreneurship skills by June,2017. |  |  | √ |  |  | 1290000 |  | 0
A01S05 | √ | √ | √ | √ | To conduct one day training on HIV/AIDS infection prevention to 40 Drug users in 3 wards by June, 2017 |  |  | √ |  |  | 1310000 |  | 0
A01S06 | √ | √ | √ | √ | To conduct one day training on reduction of HIV/AIDS infection prevention to 100 sex workers and Bar Maids in 3 Wards by June,201 |  |  | √ |  |  | 1240000 |  | 0
A01S07 | √ | √ | √ | √ | To identify 40 drug users in 3 wards by June, 2017 |  |  | √ |  |  | 300000 |  | 0
A02S01 | √ | √ | √ | √ | To promote HIV/AIDs preventive measures in community through use of condomsmin 12 Wards by June,2017. |  |  | √ |  |  | 1470000 |  | 0
A02S02 | √ | √ | √ | √ | To facilitate CHAC to attend zone meeting and seminars on HIV/AIDs by June, 2017 |  |  | √ |  |  | 2480000 |  | 0
A03S01: | √ | √ | √ | √ | To support 200 MVC with school fees and basic needs in 12 Wards by June 2017 |  |  | √ |  |  | 10680000 |  | 0
A03S02 | √ | √ | √ | √ | To facilitate and support 6 groups of PLHIV from three wards(Lyamkena Utengul and Mlowa) with grant by June, 2017 |  |  | √ |  |  | 3460000 |  | 0
A03S03 | √ | √ | √ | √ | To provide refresher training on prevention of HIV/AIDs incidence to Home Based Care in 12 Wards by June,2017 |  |  | √ |  |  | 2100000 |  | 0
A03S04 | √ | √ | √ | √ | To conduct one day training on interpreneuship skills to 12 group of PLHIV by June, 2017 |  |  | √ |  |  | 3520000 |  | 0
A04S01 | √ | √ | √ | √ | To prepare annual physical NMSF report and submmit to Rs and TAMISEMI by June,2017. |  |  | √ |  |  | 3320000 |  | 0
[5 empty] | Total for section | [5 empty] | 41661000 |  | 0
[5 empty] | Funder Total | [5 empty] | 41661000 |  | 0

## UNICEF
FUNDER CHILD SURVIVAL DEVELOPMENT PROGRAM UNICEF GRANT
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 5492 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
SECTION No: 503B: Name: POLICY AND PLANNING
SUB VOTE No: 5005 |  | SUB VOTE NAME: Planning, Trade and Economy
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: C |  | OBJECTIVE DESCRIPTION: Improve access, Quality and equitable social services delivery
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
C03C01 | √ | √ | √ | √ | To facilitates Quaterly follow up Monitoring and reports writing for council development projects by June, 2017 |  |  | √ |  |  | 13347000 |  | 0
C04C01 | √ | √ | √ | √ | To conduct 1 day training to WEOs on the preparation of O & OD and ward Quarterly financial and physical development projects reports by June, 2017 |  |  | √ |  |  | 1700400 |  | 0
C04C02 | √ | √ | √ | √ | To conduct 2 days capacity building to 4 planning staffs and 19 Heads of departments and surboninates on the importance of council statistics for the development realistic budget for sustainable council growth by June, 2017 |  |  | √ |  |  | 5240000 |  | 0
C04C03 | √ | √ | √ | √ | To facilitate 4 planning staffs to follow up and review 12 wards and 54 villages O & OD from 12 wards by June, 2017 |  |  | √ |  |  | 1170000 |  | 0
C04C05 | √ | √ | √ | √ | To conduct 3 days orientation to 4 planning staffs on utilization of council statistics for the preparation of project concept note, strategic plan and investment proposals by June,2017 |  |  | √ |  |  | 2549600 |  | 0
C04C06 |  |  |  |  | To conduct 2 day mid year reflection meeting with 15 council staffs on actual progressive relationship between council strategic plan and annual budget performance by June, 2017 | [5 empty] | 3300000 |  | 0
[5 empty] | TOTAL FOR SECTION | [5 empty] | 27307000 |  | 0
SECTION No: 507B: Name: PRIMARY EDUCATION OPERATIONS
SUB VOTE No: 5007 |  | SUB VOTE NAME: Primary Education
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D02D13 | √ | √ | √ | √ | To facilitates availability of practical trainning materials to pre-primary schools and standard I and II pupils by June,2017 |  |  | √ |  |  | 7126667 |  | 0
D02D14 | √ | √ | √ | √ | To cunduct 2 days Bi-annual school based workshops that will transform classrooms into stimulating learning environment ( Pre- standard I and II ) BY June,2017 |  |  | √ |  |  | 3800000 |  | 0
D02D15 | √ | √ | √ | √ | To conduct orientation to 12 WEOs and 38 Head Teachers on 3Rs INSET Programme and implementation modality for 4 days by June,2017 |  |  | √ |  |  | 21658000 |  | 0
D02D16 | √ | √ | √ | √ | To conduct 4 days trainning to 38 baeds mental on 3Rs INSET Programme implementation modality and mentalship by June,2017 |  |  | √ |  |  | 19400000 |  | 0
D02D17 | √ | √ | √ | √ | To conduct 2 days teachers ( Pre standard I and II ) Quarterly cluster reflection meeting on 3Rs INSET by June,2017 |  |  | √ |  |  | 5844000 |  | 0
D02D18 | √ | √ | √ | √ | To train ward and village leaders on 3Rs by June,2017 |  |  | √ |  |  | 6488000 |  | 0
D02D19 | √ | √ | √ | √ | To train 38 teachers and 76 pupils on school learning clubs by 2017 |  |  | √ |  |  | 14753333 |  | 0
D02D20 | √ | √ | √ | √ | To support WECs to carry out monthly school monitoring on INSET self study by June,2017 |  |  | √ |  |  | 7000000 |  | 0
[5 empty] | TOTAL FOR SECTION | [5 empty] | 86070000 |  | 0
SECTION No: 508A: Name: Council health management team(CHMT)
SUB VOTE No: 5010 |  | SUB VOTE NAME: HEALTH SERVICES
PROJECT CODE: 5414 |  | PROJECT NAME: Child survival and Development
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01S01 | √ | √ | √ | √ | To conduct five days training to 25 Health service providers (Nurses, Midwife, Clinician) from 10 Health facilities on IYCF by June 2017 |  |  | √ |  |  | 15580000 |  | 0
D01S02 | √ | √ | √ | √ | To conduct one day training to 20 Health workers on use of anthropometric equipment for regular nutrition assessment in 10 health facilities without SAM services by June,2017 |  |  | √ |  |  | 5030000 |  | 0
D01S03 | √ | √ | √ | √ | To organise social mobilization activities for two rounds of Vitamin A Supplementation by June 2017 |  |  | √ |  |  | 2700000 |  | 0
D01S04 | √ | √ | √ | √ | To conduct quartely iodized salt inspections to wholesale and retail shops by June 2017. |  |  | √ |  |  | 2400000 |  | 0
D01S05 | √ | √ | √ | √ | To conduct one day training to Health inspectors on quality control of iodized salt by June 2017 |  |  | √ |  |  | 1745000 |  | 0
D01S06 | √ | √ | √ | √ | Conduct nutrition advocacy meetings with DHMTs, DED, District Treasurers, DPLO, to increase resource allocation on nutrition by 2017 |  |  | √ |  |  | 1420000 |  | 0
D01S07 | √ | √ | √ | √ | To conduct quarterly supportive supervision of nutrition activities to 13 health facilities by June 2017. |  |  | √ |  |  | 11280000 |  | 0
D01S08 | √ | √ | √ | √ | To conduct bi annual Council Nutrition Steering Committee meetings by June 2017 |  |  | √ |  |  | 2525000 |  | 0
D01S09 | √ | √ | √ | √ | To develop a child Health and Nutrition months microplans in 3 days at 14 Health facilities by 2017 |  |  | √ |  |  | 7490000 |  | 0
[5 empty] | Total for section | [5 empty] | 50170000 |  | 0
[5 empty] | TOTAL FUNDER(UNICEF) | [5 empty] | 163547000

## CARRY OVER
MAKAMBAKO TOWN COUNCIL
FIRST QUARTER ( JULY - SEPTEMBER,2016) PROGRESS REPORT FOR THE FINANCIAL YEAR 2016/2017
OWN SOURCE FUND
CARRY OVER ACTIVITIES FOR THE FINANCIAL YEAR 2015/2016
SECTION No: 502D: Name Finance Revenue
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SUB VOTE No: 5000 |  | SUB VOTE NAME: Administration and General
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2015/2016
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: C |  | OBJECTIVE DESCRIPTION: Improve access, quality and equitable social services delivery
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Carry over Fund | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| √ | √ | √ | √ | To buy 5 revenue collections machines in the council by june, 2017 | [5 empty] | 6000000 |  | 0
| √ | √ | √ | √ | Construction of 1195 Desks for Primary schoos by june,2017 | [5 empty] | 15819000 |  | 0
[5 empty] | Total for Section | [5 empty] | 21819000 |  | 0
[5 empty] | Total -OWN-SOURCE | [5 empty] | 21819000 |  | 0
CARRY OVER ACTIVITIES FOR THE FINANCIAL YEAR 2015/2016
LOCAL GOVERNMENT DEVELOPMENT GRANT-LGDG (CDG)
SECTION No: 500A Name: Administration General
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SUB VOTE No: 5000 |  | SUB VOTE NAME: Administration and General
PERIOD COVERED: |  | Quarter ending September, 2016 in the Financial Year 2015/2016
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Carry over Fund | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| √ | √ | √ | √ | To construct Makambako Town Council Office by June,2017 |  |  | √ |  |  | 132218411.97
[5 empty] | Section Total | [5 empty] | 132218411.97 | 0
[5 empty] | Total - (LGDG) | [5 empty] | 132218411.97 | 0
CARRY OVER ACTIVITIES FOR THE FINANCIAL YEAR 2015/2016
DEVELOPMENT PROJECTS FINANCED BY NWSSP FUND
SECTION No: 510A: NAME: Rural Water Supply
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE : NO:2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SUB VOTE CODE: 5017 |  | SUB VOTE NAME |  |  | RURAL WATER SUPPLY
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2015/2016
PROJECT CODE: 3280 |  | PROJECT NAME: |  |  | RURAL WATER SUPPLY AND SANITATION
OBJECTIVE CODE:C |  | OBJECTIVE DESCRIPTION: Improve access quality and equitable social services delivery
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Carry over Fund | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| √ | √ | √ | √ | To construct Manga village gravity water scheme by June 2017 |  |  | √ |  |  | 235347761.1 |  | 0
[5 empty] | Total for section | [5 empty] | 235347761.1 |  | 0
[5 empty] | Total - NWSSP | [5 empty] | 235347761.1 |  | 0
CARRY OVER ACTIVITIES FOR THE FINANCIAL YEAR 2015/2016
FUNDER NATIONAL MULTISECTORAL STRATEGIC FUND (NMSF)
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 5492 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SECTION No: 527B: Name :Community Development,Gender and Children
SUB VOTE No: 5027 |  | SUB VOTE NAME: Comm Dvt,Gender and Children
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
PROJECT CODE: 5492 |  | PROJECT NAME: Tanzania Multisectoral HIV/AIDS Project
OBJECTIVE CODE:A |  | OBJECTIVE DESCRIPTION: Improve Services and reduce HIV/AIDS Project
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Carry over Fund | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| √ | √ | √ | √ | To facilitate HIV/AIDS activities by June, 2017 |  |  | √ |  |  | 43692058 |  | 0
[5 empty] | Total for section | [5 empty] | 43692058 |  | 0
[5 empty] | Total - NMSF | [5 empty] | 43692058 |  | 0
CARRY OVER ACTIVITIES FOR THE FINANCIAL YEAR 2015/2016
FUNDER COUNCIL DEVELOPMENT COMMUNITY FUND (CDCF)
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 5492 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Carry over Fund | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| √ | √ | √ | √ | To facilitate activities finanvced by CDCF by June, 2017 |  |  | √ |  |  | 4181000 |  | 0
[5 empty] | Total for section | [5 empty] | 4181000 |  | 0
[5 empty] | Total - CDCF | [5 empty] | 4181000 |  | 0
CARRY OVER ACTIVITIES FOR THE FINANCIAL YEAR 2015/2016
FUNDER HEALTH SECTOR BASKET FUND (HSBF)
SECTION No: 5010 Name: HEALTH
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 5492 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SUB VOTE No: 508A |  | SUB VOTE NAME: Council Hospital Services
PROJECT CODE: 3218 |  | PROJECT NAME: HEALTH SECTOR BASKET FUND
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2015/2016
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activity Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Carry over Fund | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| √ | √ | √ | √ | To facilitate activities finanvced by Health sector Basket fund (HSBF) by June, 2017 |  |  | √ |  |  | 36595255.01 |  | 0
[5 empty] | Total for section | [5 empty] | 36595255.01 |  | 0
[5 empty] | Total - HSBF | [5 empty] | 36595255.01 |  | 0
CARRY OVER ACTIVITIES FOR THE FINANCIAL YEAR 2015/2016
TANZANIA SOCIAL ACTION FUND - TASAF
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SECTION No: 527A Name: Community development, Youth and Social welfare Administration
SUB VOTE No: 5027 |  | SUB VOTE NAME: community development, Gender and Children
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2015/2016
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To facilitate the actvities financed by Tanzania Social Action Fund by June(TASAF), 2017 |  |  | √ |  |  | 128490102.9 |  | 0
[5 empty] | Total for section | [5 empty] | 128490102.9 |  | 0
[5 empty] | Total - TASAF | [5 empty] | 128490102.9 |  | 0
CARRY OVER ACTIVITIES FOR THE FINANCIAL YEAR 2015/2016
FUNDER ROAD FUND
SECTION No: 511B: Name: Road Services
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SUB VOTE No: 5014 |  | SUB VOTE NAME: Works
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
PROJECT CODE: 4101 |  | PROJECT NAME: Road Sector Programme Support
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Activirty Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To cary out 15 KM of routine maintainance at Makambako Town street Roads( Kiumba street 5Km, Makambako Town 10Km) by Juni 2017 |  |  | √ |  |  | 19410000 |  | 0
D01D02 | √ | √ | √ | √ | To cary out 37Km of sport improvement at Makambako Town Council (Makambako -Ibumila,Malombwe-Mkolango, Kifumbe-Igongolo, Manga-Igongolo) ifikapo Juni 2017 |  |  | √ |  |  | 52696667 |  | 0
D01D03 | √ | √ | √ | √ | To cary out 16.2Km of sport improvement at Makambako Town Council (Makambako street 2 Km, Ubena sreet 3Km, Mjimwema 3Km, Kiumba-Ngamanga Road 8.2 Km) By Juni 2017 |  |  | √ |  |  | 55576832 |  | 0
D02D01 | √ | √ | √ | √ | Tonstruct 2 Bridges/Drift (2 Bridge along Makambako-Ibumila-Mtulingala Roads,2 culverts along Manga-Igongolo Road and 1 Curvert along Kifumbe, Igongolo Roads by Juni 2017 |  |  | √ |  |  | 149168000 |  | 0
D02D03 | √ | √ | √ | √ | Follow up and Supervision of Roads and Brides construction by Juni 2017 |  |  | √ |  |  | 25034800 |  | 0
[5 empty] | Total for secton | [5 empty] | 301886299 |  | 0
[5 empty] | Total -ROAD FUND | [5 empty] | 301886299 |  | 0

## BASKET FUND
b
FUNDER HEALTH SECTOR BASKET FUND (HSBF)
SECTION No: 5010 Name: HEALTH
SUB VOTE No: 508A |  | SUB VOTE NAME: Council Hospital Services
PROJECT CODE: 3218 |  | PROJECT NAME: HEALTH SECTOR BASKET FUND
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To facilitate the actvities financed by Health sector Basket Fund by June, 2017 |  |  | √ |  |  | 189502000 | 0 | 0
[5 empty] | Total for Section | [5 empty] | 189502000

## TASAF
TANZANIA SOCIAL ACTION FUND - TASAF
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SECTION No: 527A Name: Community development, Youth and Social welfare Administration
SUB VOTE No: 5027 |  | SUB VOTE NAME: community development, Gender and Children
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: D |  | OBJECTIVE DESCRIPTION: Increase quantity and Quality of social services and Infrastructure
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To facilitate the actvities financed by Tanzania Social Action Fund by June, 2017 |  |  | √ |  |  | 849774000 | 0 | 0
[5 empty] | Total for Section | [5 empty] | 849774000

## ASDP
AGRICULTURAL SECTOR DEVELOPMENT PROGRAM-(ASDP)
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
SECTION No: 506B Name: Agriculture Operations
SUB VOTE No: 5033 |  | SUB VOTE NAME: Agriculture
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
PROJECT CODE: 3218 |  | PROJECT NAME: Agriculture Sector Development program suport
OBJECTIVE CODE: C |  | OBJECTIVE DESCRIPTION:Improve access, Quality and equitable social services delivery
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D01D01 | √ | √ | √ | √ | To facilitate the actvities financed by Agricultural sector development program (ASDP) by June, 2017 |  |  | √ |  |  | 74081000 |  | 0
[5 empty] | Total for Section | [5 empty] | 74081000

## NWSSP
FUNDER NATIONAL WATER SUPPLY AND SANITATION PROGRAM (NWSSP)
VOTE CODE: 54 |  | VOTE NAME: NJOMBE REGION
SUB VOTE CODE: 2028 |  | SUB VOTE NAME: MAKAMBAKO TOWN COUNCIL
PERIOD COVERED: |  | Quarter ending September,2016 in the Financial Year 2016/2017
SECTION No: 510A: Name: Rural Water Supply
SUB VOTE No: 5017 |  | SUB VOTE NAME:Rural Water Supply
PROJECT CODE: 3280 |  | PROJECT NAME: Rural water supply and sanitation
OBJECTIVE CODE: C |  | OBJECTIVE DESCRIPTION:Improve access, Quality and equitable social services delivery
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
CO4DO1 | √ | √ | √ | √ | To construct Mtulingala village gravity water scheme by June 2017 |  |  | √ |  |  | 69836000 |  | 0
CO4D02 | √ | √ | √ | √ | To facilitate monitoring and supervision of Mtulingala gravity water scheme by June 2017 |  |  | √ |  |  | 3000000 | 0 | 0
[5 empty] | Total for section | [5 empty] | 72836000 |  | 0
SECTION No: 501A: Name: Environments and cleansing Administration
SUB VOTE No: 5036 |  | SUB VOTE NAME: ENVIRONMENT
PROJECT CODE: 3218 |  | PROJECT NAME: District Development Project
OBJECTIVE CODE: C |  | OBJECTIVE DESCRIPTION:Improve access, Quality and equitable social services delivery
CODES AND LINKAGES |  |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | Remarks on Implementation
Target Code | FYP | M | P | R | Activity Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Annual Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
C07S01 | √ | √ | √ | √ | To conduct advocacy sessions to 24 WDC leaders and influential people to solicity support on NSC by June 2017 |  |  | √ |  |  | 2188000 |  | 0
C07S02 | √ | √ | √ | √ | To conduct orientation session to 20 VHWs, 8VCs,8VEOs and 2WEOs on baseline data collection and compilation by June 2017 |  |  | √ |  |  | 1968500 |  | 0
C07S03 | √ | √ | √ | √ | To conduct baseline data collection for household sanitation in 30 sub villages by June 2017 |  |  | √ |  |  | 4000000 |  | 0
C07S04 | √ | √ | √ | √ | To conduct training of 5 CLTS facilitators |  |  | √ |  |  | 936000 |  | 0
C07S05 | √ | √ | √ | √ | To conduct follow up missions on 36 signed community declarations by June 2017 |  |  | √ |  |  | 1220000 |  | 0
C07S06 | √ | √ | √ | √ | To conduct 10 days training to 25 artisans from villages that implement the NSC by June 2017 |  |  | √ |  |  | 4361500 |  | 0
C07S07 | √ | √ | √ | √ | To orient 3 groups on the concept of NSC by June 2017 |  |  | √ |  |  | 3295000 |  | 0
C07S08 | √ | √ | √ | √ | To engage 2 credible groups for promotion NSC by June 2017 (Environment Day, Water week and Toilet Day) |  |  | √ |  |  | 3290000 |  | 0
C08S01 | √ | √ | √ | √ | To conduct supervision/follow up for 2 schools by June 2017 |  |  | √ |  |  | 487500 |  | 0
C08S03 | √ | √ | √ | √ | Rehabilitation of toilets/ latrine for 2 schools by June 2017 |  |  | √ |  |  | 12253500 |  | 0
[5 empty] | Total for section | [5 empty] | 34000000 |  | 0
[5 empty] | FUNDER TOTAL (NWSSP) | [5 empty] | 106836000 |  | 0